## Sheet1
Task | Priority | Status | Start date | End date | Notes | Completed by
Group roles | P3 | Completed | 2025-11-07 | 2025-11-07 | No issues with roles assigned | Kate, Ethan | Note: P0 = highest, P3 = lowest
Set up testing sheet | P3 | Completed | 2025-11-11 | 2025-11-11 | Blank testing sheet complete. Ready for testing | Kate
Project vision document | P3 | Completed | 2025-11-07 | 2025-12-02 | Final draft complete + on the GitHub. Needs to be signed off | Kate, Ethan
Market research | P3 | Completed | 2025-11-10 | 2025-11-10 |  | Kate, Tyler
Scope/requirements | P3 | Completed | 2025-11-11 | 2025-11-25 |  | Kate, Ethan, Dan, Tyler
Wireframes | P0 | In progress | 2025-11-24 |  |  | Dan
Use case diagram | P3 | Completed | 2025-12-01 |  |  | Tyler
ERD | P3 | Completed | 2025-12-07 | 2025-12-07 |  | Tyler
Normalisation | P1 | In progress
Field definition grid | P1 | In progress
Feedback/testing | P2 | Not started
Prototype | P1 | In progress